## Product Backlog
Product Backlog - Team Hearts
Name of the Software: | Pace University Shuttle App
Product owner: | Thomas Schmidt
Date of creation: | 2020-09-14
ID | Name | Creation Date | Description | Size | Priority | Dependencies | Notes | Sprint
US1 | Account Registration | 2020-09-17 | User: Create an account to have access to the app | Medium | high |  |  | 1
US2 | Login | 2020-09-17 | User: Be able to access the app with account | Medium | high | US1 |  | 1
US3 | Track Locations | 2020-09-17 | User: Know where shuttles are/where riders are | Medium | low | US4 |  | 1
US4 | Shuttle Map | 2020-09-17 | User: Know where shuttles are/where riders are | Medium | medium |  |  | 1
US5 | Place Reservations | 2020-09-17 | User: Riders to reserve spots on the shuttle in efficient way through app | Large | high | US5
US6 | Cancel Reservations | 2020-09-17 | User: Riders can cancel their reservations if they they cannot make it | Medium | high
US7 | 1 Minute Away Button | 2020-09-17 | User: Emergency, I'm almost there don't leave without me button | Small | medium
US8 | Shuttle Leaving Button | 2020-09-17 | User: Driver informing people that shuttle is leaving through app to people who signed up and didn't make it | Medium | medium
US9 | Request Counter | 2020-09-17 | Administration: Know data on when most people want to use shuttle/actual users of the shuttle | Small | medium
US10 | View Schedule | 2020-09-17 | User: Know shuttle schedule | Medium | high
US11 | Adjust Schedule | 2020-09-17 | User: Drivers/supervisors can adjust schedule | Medium | low | US10
US12 | Account types | 2020-09-17 | User: Different capabilities and information for different classifications of user: driver, passenger, supervisor | Large | medium
US13 | View shuttle capacity | 2020-09-17 | User: Potential passengers know if there are seats available; drivers know how many to expect; supervisors know use | Medium | high
US14 | Detect potential delay in route | 2020-09-17 | User: Able to anticipate and then respond to traffic/delays | Large | low | US4, US3
US15 | Suggest alternate route | 2020-09-17 | User: Drivers able to use faster route | Medium | low | US14
US16 | Alert Delay | 2020-09-17 | User: User will be alerted of delay and new eta, and will be able to easily forward this information | Large | low | US14
US17 | Create framework | 2020-09-17 | Developer: skeleton to build functionalities on | Large | high |  |  | 1
US18 | Create AWS PostGres Server | 2020-09-28 | Developer: create database to be used |  | high
US19 | AWS Infrastructure | 2020-09-28 |  |  |  | US18
US20 | Interview Transportation Dept. | 2020-09-28 | Developer: Refine specs with input from potential users / knowledgeable parties | small | medium
US21 | Android Studio Training | 2020-09-28 | Developer: All team members will understand android studio use | large | high
US22 | Basic access and use of PostGres server | 2020-09-28 | Developer: All team members will be able to utilize database | medium? | medium | US18
|  |  |  | Medium | High |  | Firebase Login system | 1
|  |  |  | Medium | High | This is the main activity | Bottom app navigation menu | 1
|  |  |  | Medium | Medium | US2 | Google Maps API | 1
|  |  |  | Large | High | US 3, US 14 | Draw Route in Maps | 1
|  |  |  | Medium | Medium | US 3, US 10 | Connect to database, parse locations, and display pin on map | 2
|  |  |  | Medium | Medium | US 3, US 10 |  | 1
|  |  |  | Large | Medium | US 4 |  | 2
|  |  |  | Large | Low | US 5 |  | 2
|  |  |  | Large | Low | US 6 |  | 2
|  |  |  | Small | High |  |  | 1
|  |  |  | Small | Low |  |  | 2
|  |  |  | Medium | Low | US5
|  |  |  | Small | Medium | US1 | Keep user logged in | 2
|  |  |  | Medium | High |  |  | 1
|  |  |  | Small | Medium | US1 |  | 2
|  |  |  | Medium | High | US2 |  | 1
|  |  |  | Medium | High | US2 |  | 1
|  |  |  | Medium | High |  |  | 1
|  |  |  | Medium | High |  |  | 1
|  |  |  | Medium | High |  |  | 1
|  |  |  | High | High |  |  | 2
|  |  |  | Low | Low |  |  | 2
|  |  |  | Medium | Medium |  |  | 3
|  |  |  | Medium | High |  |  | 3
|  |  |  | Medium | High |  |  | 3
|  |  |  | Medium | High |  |  | 3
|  |  |  | Low | High |  |  | 3
|  |  |  | Low | Medium
|  |  |  | Medium | High |  |  | 4
|  |  |  | Medium | Medium
|  |  |  | Medium | Medium |  |  | 4
|  |  |  | Medium | High |  |  | 4
4

## Sprint 1 Backlog
Sprint 1 Backlog Scrum Master: Dean
TASK ID | TASK DESCRIPTION | DIFFICULTY RATING | ISSUES | COMPLETED
US1 | Account Registration | 2
US2 | Login | 2
US3 | Track Locations | 3
US4 | Shuttle Map | 3
US17 | Create framework | 4

## Sprint 2 Backlog
Sprint 2 Backlog Scrum Master: Anna
TASK ID | TASK DESCRIPTION | DIFFICULTY RATING | ISSUES | COMPLETED | GOAL
US 21 | Complete Android training | 1
US18 | Create AWS postgres server | 3
US19 | AWS infrastructure | 3
US 22 | Basic access & use of server | 2
US1A | Identify more registration subtasks | 1
US2A | Identify more login subtasks | 1
US20 | Transportation dept interview | 1
US20A | Update specs from interview input | 1
US1 | Account Registration | 4 |  |  | Prototype working registation and login in Android Studio
US2 | Login | 4 |  |  | and connect this with AWS database

## Sprint 3 Backlog
Sprint 3 Backlog Scrum Master:
TASK ID | TASK DESCRIPTION | DIFFICULTY RATING | ISSUES | COMPLETED

## Sprint 4 Backlog
Sprint 4 Backlog Scrum Master:
TASK ID | TASK DESCRIPTION | DIFFICULTY RATING | ISSUES | COMPLETED

## Sprint 5 Backlog
Sprint 5 Backlog Scrum Master:
TASK ID | TASK DESCRIPTION | DIFFICULTY RATING | ISSUES | COMPLETED